## Phase 0 - Baseline, safety net and engineering governance

Establish an objective baseline so refactoring can prove that behavior, performance and visual output have not regressed.

### Work items

Run and record the complete PHP test suite; separate pre-existing failures from refactor failures.

Capture representative screenshots for Dashboard, Orders list/detail/task, Inquiry list/detail/task, My Work, Master Data, Product/Category, Client, Documents and key responsive widths.

Record request latency, query count/query time, memory and cache metrics for the busiest workflows using the existing performance monitor.

Record frontend bundle/CSS transfer sizes and browser performance snapshots.

Introduce source architecture budgets: giant-file line count, Blade style/app/auth calls, !important count, hard-coded color count and legacy CSS size.

Add formatting/static-analysis tooling and a CI skeleton if not already available in the deployment repository.

Document database backup/restore procedure before structural migrations.

### Deliverables

Baseline report

Approved visual baselines

Architecture budget script

CI quality-gate skeleton

Refactor branch/release procedure

### Exit / acceptance criteria

✓ Current production workflows have a recorded baseline.

✓ Any existing failing test is documented.

✓ Metrics can be re-run deterministically.

✓ No structural refactor starts without visual and functional regression coverage.

| Risk | Rollback principle |
| --- | --- |
| Low | No functional change; rollback is removal of tooling only. |

## Phase 1 - Central design tokens and global CSS foundation

Create a single authoritative location for shared colors, typography, spacing, borders, radius, shadows, motion and base application styling.

### Work items

Create foundation/tokens.css and foundation/global.css.

Define brand, semantic and neutral color scales plus semantic aliases for page/surface/text/border roles.

Define font family, size, weight and line-height scale.

Define spacing, radius, shadow, z-index, transition and focus-ring scales.

Create reduced-motion and focus-visible defaults.

Create app.css as a composition entry instead of a monolithic implementation file.

Add an explicit legacy stylesheet boundary; freeze existing compatibility CSS so its budgets cannot increase.

Document token naming and permitted usage.

### Deliverables

tokens.css

global.css

app.css composition root

legacy CSS boundary

docs/ui-design-system.md token section

### Exit / acceptance criteria

✓ One authoritative static design-token source exists.

✓ New shared UI does not introduce hard-coded design values.

✓ No approved page should visually change yet.

✓ Legacy CSS budgets are frozen and measurable.

| Risk | Rollback principle |
| --- | --- |
| Low | Remove new imports and return to the current stylesheet entry; no business logic/data changes. |

## Phase 2 - Reusable CSS and Blade UI component library

Turn the token system into stable, accessible, reusable UI contracts used throughout FlowTrack.

### Work items

Create centralized styles and Blade components for buttons, icon buttons, badges, form fields, dropdowns, cards, tables, tabs, modals, tooltips, pagination, loading, empty and validation states.

Normalize existing ui components rather than duplicating them.

Build loading/disabled/focus/hover/error states into the component API.

Add runtime-color support for workflow/status/priority/department components.

Create component demos or a developer-only style reference page for visual inspection.

Add tests/static scans that prevent new page-level reimplementations.

### Deliverables

components.css and component partials

Official resources/views/components/ui contracts

Component reference documentation

Architecture tests for prohibited styling patterns

### Exit / acceptance criteria

✓ All foundational component types have one official implementation.

✓ Keyboard focus and disabled/loading behavior are defined.

✓ Runtime Master Data colors still work.

✓ New feature work can build a page without inventing component CSS.

| Risk | Rollback principle |
| --- | --- |
| Low-Medium | Components can coexist with legacy markup until each page is migrated. |

## Phase 3 - Incremental legacy CSS and page migration

Remove duplicated/conflicting CSS in controlled batches while keeping the UI visually stable.

### Work items

Migrate globally repeated header/sidebar/filter/button/form patterns first.

Migrate Orders, My Work and All Tasks as the first feature family because they share many visual patterns.

Migrate Inquiries and Inquiry Intelligence next.

Migrate Dashboard/reporting, then Clients/Catalog, then Master Data/Workflow/Task Packs/Admin.

For every batch: replace component markup, compare screenshots at desktop/tablet/mobile, run feature tests, then delete replaced legacy selectors.

Remove the split-flowtrack-css mechanism only after flowtrack.css is no longer the canonical source.

Move Vite to one shared composition root plus narrowly scoped feature entries only where transfer size materially benefits.

### Deliverables

Migrated feature batches

Reduced legacy stylesheet

Simplified Vite input/configuration

Per-batch visual regression evidence

### Exit / acceptance criteria

✓ No page-level duplicate component styling remains in migrated areas.

✓ Legacy !important/hard-coded-color budgets decrease every batch.

✓ No visual regression is accepted without explicit approval.

✓ Generated flowtrack-01..04 chunks can ultimately be deleted.

| Risk | Rollback principle |
| --- | --- |
| Medium | Each feature batch is a separate commit/release unit; revert one batch without reverting the design foundation. |

## Phase 4 - Shared forms, filters, search and selection architecture

Unify the interaction patterns that currently recur throughout Orders, Inquiries, reports, Master Data and user assignment.

### Work items

Create one searchable single-select API and one multi-select API, with remote pagination for large datasets.

Create one date/date-range field API, one search input, one filter chip/bar system and one clear/reset pattern.

Centralize validation display, server error state and inline save state.

Remove duplicated assignee/client/department/status selector implementations.

Ensure selectors are bounded and do not preload full user/product/client catalogs.

Define keyboard behavior and ARIA semantics once.

### Deliverables

RemoteSelect/SearchSelect component

FilterBar primitives

DateRange component

Unified validation/helper text patterns

Selector query contracts

### Exit / acceptance criteria

✓ Equivalent controls behave and look the same across modules.

✓ Large lookup lists are remote/bounded.

✓ A filter does not load unrelated data.

✓ No random fallback results appear when a search has no match.

| Risk | Rollback principle |
| --- | --- |
| Medium | Keep feature-specific adapters translating old Livewire property names to new components until stable. |